## BackEnd
No | Submenu | Activity | Status | Status
1 | Registration | Manage user regist with all condition | 100% | OK
2 | Forgot Password | Manage user password with all condition | 100% | OK
3 | Dashboard | show table | 0%
4 | Dashboard | show chart | 0%
5 | Manage User | Add | 70% | Validation email, null(required)
6 | Manage User | Edit | 0%
7 | Manage User | Delete | 0%
8 | Manage User | Read | 80%